## Initialization
Meeting: |  | TOD evening (~7pm)
|  | Brandy | Wouter | Hitesh | Daniel | Kim | Ranga | Harwinder
Best Meeting Times: | Tues | X
| Thurs | X |  | X
| Friday | X | X | X(FROM 8:15PM)
| Saturday | X | X | X(FROM 8:15PM)
| Sunday | X | X | X
Areas of Focus
| Harwinder | Climate change effect on Immigration
Kim
| Wouter | -- Euro (certain countries are closing borders and other countries have to take the immigrants), search how the European Union integrate and assumulate immigrants | [6 empty] | https://ec.europa.eu/eurostat/web/population-demography-migration-projections/data/database
| Brandy | Flow of immigration (in and out), refuge and illegal immigration
Ranga
| Daniel | Economic (GDP, GNI, NNI) impact of immigrants
Hitesh
| Thoughts: | Initial Focus -- volume of immigrants from and where are they going
Distinguish between economic and political immigrants
Identify Roles
Level of Effort | Take a role (please select your strength)
Meeting note-taker:
Meeting Coordinator:
Person responsible for the group submissions:
| Literature Final Review Editor: | Wouter
Methodology Final Review Editor:
Analysis Final Review Editor:
| Final Editor: | Brandy (I'll take this one since I've already completed my masters and the rest of you have other classes and finals around the same time)

## Timeline
Dr. P Due Date | Sub Group Date | Peer Review Complete Date | TASK
Identify Subgroup Topics
Identify Data Set to Use
Literature Review (what other studies are out there that are similar to bring context to what we're doing)
Methodology
Analysis
Findings
"Put full paper together" (there will be a lot of sub-pieces)
February 27th | 2019-02-25 | 2019-02-26 | Group Project Review and Feedback 1
This is a short timeline with about 1 day turn around for feedback
I *THINK* it is reasonable to have 1-3 pages per subgroup put together and an outline for what kind of analysis you want to complete
March 28th | 2019-03-20 | 2019-03-25 | Group Review and Feedback 2
This gives 3 days for sub group to incorporate peer review feedback
I think it's reasonable to have the analysis and findings almost complete by this time.
April 30th | 2019-04-15 | 2019-04-25 | Final Report Due
This provides 20 days to complete "sub group" and then 10 days to peer review another sub group and then 5 days for the final editor to put the whole thing together.